## Slide 1: Scheduling
12 September 2012

## Slide 2: SCHEDULING

## Slide 3: “80% of software projects fail”
Standish Report (1995)
  16.2% completed on-time and on-budget with all features and functions as initially specified.
  52.7% completed and operational but over-budget, over the time estimate, and offers fewer features and functions than originally specified.
  31.1% cancelled at some point during the development cycle.
Sauer et al (2007)
  67% “delivered close to budget, schedule, and scope expectations” with experienced project managers

## Slide 4: Project Management
Discipline of
planning,
organizing, and
managing resources
to bring about
the successful completion of
specific project goals and objectives

## Slide 5: Should we eliminate risk?
Patton: Take calculated risks. That is quite different from being rash.
Nehru: The policy of being too cautious is the greatest risk of all.
Herodotus: Great deeds are usually wrought at great risks.
The Net: No risk => no challenge

## Slide 6: Sources of Risk
Top management commitment
User commitment
Misunderstood requirements
Inadequate user involvement
Mismanaged user expectations
Scope creep
Lack of knowledge or skill
  Keil et al, “A Framework for Identifying Software Project Risks,” CACM 41:11, November 1998

## Slide 7: Technical Risks
New features
New technology
Developer learning curve
Changes that may affect old code
Dependencies
Complexity
Bug history
Late changes
Rushed work
Tired programmers
Slipped in “pet” features
Unbudgeted items

## Slide 8: Scheduling
Process
Within the Steps
Put together minimal solution
  Start with external commitments
  Introduce internal milestones
Focus on the risks
Add next level of features where possible
Identify components
Identify dependencies
Estimate (guess)
  Prefer educated guess
Lay out assignments and time frames

## Slide 9: Project Plan for this project
Use simple Excel spreadsheet (or equivalent)
Deliverable/Milestone | Responsible | Due | Revision 1 | Delivered
project web site | Sam | 20-Jan |  | 20-Jan
architecture | Jane (all) | 8-Feb | 15-Feb | 23-Feb
project plan | Harry | 10-Feb | 15-Feb | 16-Feb
initial user interface | Sam | 13-Feb | 15-Feb | 18-Feb
contract | Jane | 20-Feb | 15-Feb | 18-Feb

## Slide 10: Questions project plan answers
What is Joe working on this week?
Who can help me if I run into trouble?
If I have to choose an activity to be late, which one will impact the project more?

## Slide 11: What needs to be in the plan?
All Deliverables
Code
Design
Test
Documentation
Learning
Presentation and demo prep
Reviews

## Slide 12: REVIEWS AND INSPECTIONS

## Slide 13: Reviews and Inspections
Why?
  Developer can’t correct unseen errors
  More eyes to catch problems
  Earlier is cheaper
    Integration fix typically 3-10 times the cost at design
Difference in terms
  Review implies completed work, often reviewed by someone at a different level
  Inspection implies peer review of work in progress

## Slide 14: Inspections
Introduced by Michael Fagan in 1976 (IBM Systems Journal)
Formalized process
  Specific roles and steps
  Heavy preparation and follow-up
Used for documents and code
  In 1999, survey identified 117 checklists covering requirements, design, code, testing, documentation and process